## PV
[Project Title] | [13 empty] | [Company Name / Logo]
Earned Value Analysis Report
| Prepared By: | [Manager's Name]
| Date: | [Report Date]
[42]
| For Period: | Week 1
Summary:
El periodo indica semana terminada
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | Licitación | 0 | [15 empty] | ← Enter or edit values in the light-blue cells.
1.1.1 | Propuestas | 200000 | 200000
1.1.2 | Dispositivos | 3000000 | 3000000
1.2 | Diseño arquitectura/centro de datos | 0
1.2.1 | Habitación/sector | 500000 | 500000
1.2.2 | Validar diseño | 200000 | 200000
1.2.3 | Instalar dispositivos | 300000 |  | 300000
1.2.4 | Contrato con IPS | 200000 |  | 200000
1.3 | Pruebas de Compatibilidad | 0
1.3.1 | Informe | 300000 |  | 300000
1.4 | Software | 0
1.4.1 | Análisis de software | 0
1.4.1.1 | Alcance del producto | 100000 |  | 100000
1.4.1.2 | Objetivos | 50000 |  | 50000
1.4.1.3 | Análisis FODA | 50000 |  | 50000
1.4.2 | Especificaciones de requerimientos | 0
1.4.2.1 | Requerimientos | 0
1.4.2.1.1 | Funcionales | 100000 |  | 100000
1.4.2.1.2 | No fucionales | 100000 |  | 50000 | 50000
1.4.3 | Codificación | 2100000 |  |  |  | 700000 | 700000 | 700000
1.4.4 | Pruebas | 0
1.4.4.1 | Casos de pruebas | 1000000 | [6 empty] | 1000000
1.4.4.2 | Instalación de software | 300000 | [7 empty] | 300000
1.4.4.3 | Pruebas de usuario | 10000000 | [8 empty] | 5000000 | 5000000
1.4.4.4 | Manual de usuario | 200000 | [10 empty] | 200000
1.4.4.5 | Capacitación | 400000 | [11 empty] | 400000
1.5 | Migración | 0
1.5.1 | Planificación | 1000000 | [12 empty] | 1000000
1.5.2 | Planes de contingencia | 1000000 | [13 empty] | 1000000
Insert new rows above this one
| Total Budgeted Cost | 4850000 | 3900000 | 1150000 | 50000 | 700000 | 700000 | 700000 | 1000000 | 300000 | 5000000 | 5000000 | 200000 | 400000 | 1000000 | 1000000
|  | Cumulative Planned Value (PV) | 3900000 | 5050000 | 5100000 | 5800000 | 6500000 | 7200000 | 8200000 | 8500000 | 13500000 | 18500000 | 18700000 | 19100000 | 20100000 | 21100000
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 4700000 | 5840000 | 5870000 | 6770000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000
|  | Cumulative Earned Value (EV) | 160000 | 4650000 | 100000 | 2100000 | 1680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -4540000 | -1190000 | -5770000 | -4670000 | -5690000 | -7370000 | -7370000 | -7370000 | -7370000 | -7370000 | -7370000 | -7370000 | -7370000 | -7370000 | Línea azul en el gráfico
|  | Schedule Variance (SV = EV - PV) | -3740000 | -400000 | -5000000 | -3700000 | -4820000 | -7200000 | -8200000 | -8500000 | -13500000 | -18500000 | -18700000 | -19100000 | -20100000 | -21100000
|  | Cost Performance Index (CPI = EV/AC) | 0.034043 | 0.79623 | 0.017036 | 0.31019 | 0.22795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Schedule Performance Index (SPI = EV/PV) | 0.041026 | 0.92079 | 0.019608 | 0.36207 | 0.25846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Línea roja en el gráfico
|  | Estimated Cost at Completion (EAC) | 142468750 | 6091182.7957 | 284695000 | 15635476.1905 | 21276488.0952 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Línea verde en el gráfico
Fecha oficial inicio de proyectos |  |  | 2015-04-10
Fecha presentación de proyectos terminados |  |  | 2015-07-17
Total semanas |  |  | 14
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)
Note on D21: profesor: 10/04/15 al 17/04/15

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Licitación | 0
1.1.1 | Propuestas | 200000 | 80%
1.1.2 | Dispositivos | 3000000 |  | 100%
1.2 | Diseño arquitectura/centro de datos | 0
1.2.1 | Habitación/sector | 500000 |  | 75%
1.2.2 | Validar diseño | 200000 |  | 90%
1.2.3 | Instalar dispositivos | 300000 |  | 100%
1.2.4 | Contrato con IPS | 200000 |  | 100%
1.3 | Pruebas de Compatibilidad | 0
1.3.1 | Informe | 300000 |  | 80%
1.4 | Software | 0
1.4.1 | Análisis de software | 0
1.4.1.1 | Alcance del producto | 100000 |  | 90%
1.4.1.2 | Objetivos | 50000 |  | 90%
1.4.1.3 | Análisis FODA | 50000 |  | 80%
1.4.2 | Especificaciones de requerimientos | 0
1.4.2.1 | Requerimientos | 0
1.4.2.1.1 | Funcionales | 100000 |  | 95%
1.4.2.1.2 | No fucionales | 100000 |  | 85% | 100%
1.4.3 | Codificación | 2100000 |  |  |  | 100% | 80%
1.4.4 | Pruebas | 0
1.4.4.1 | Casos de pruebas | 1000000
1.4.4.2 | Instalación de software | 300000
1.4.4.3 | Pruebas de usuario | 10000000
1.4.4.4 | Manual de usuario | 200000
1.4.4.5 | Capacitación | 400000
1.5 | Migración | 0
1.5.1 | Planificación | 1000000
1.5.2 | Planes de contingencia | 1000000
Insert new rows above this one
|  | Cumulative EV | 160000 | 4650000 | 100000 | 2100000 | 1680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Licitación
1.1.1 | Propuestas |  | Wk 1: 250000
1.1.2 | Dispositivos |  | Wk 1: 4000000
1.2 | Diseño arquitectura/centro de datos
1.2.1 | Habitación/sector |  | Wk 1: 300000
1.2.2 | Validar diseño |  | Wk 1: 150000
1.2.3 | Instalar dispositivos |  | Wk 2: 300000
1.2.4 | Contrato con IPS |  | Wk 2: 300000
1.3 | Pruebas de Compatibilidad
1.3.1 | Informe |  | Wk 2: 200000
1.4 | Software
1.4.1 | Análisis de software
1.4.1.1 | Alcance del producto |  | Wk 2: 80000
1.4.1.2 | Objetivos |  | Wk 2: 50000
1.4.1.3 | Análisis FODA |  | Wk 2: 50000
1.4.2 | Especificaciones de requerimientos
1.4.2.1 | Requerimientos
1.4.2.1.1 | Funcionales |  | Wk 2: 90000
1.4.2.1.2 | No fucionales |  | Wk 2: 70000; Wk 3: 30000
1.4.3 | Codificación |  | Wk 4: 900000; Wk 5: 600000
1.4.4 | Pruebas
1.4.4.1 | Casos de pruebas
1.4.4.2 | Instalación de software
1.4.4.3 | Pruebas de usuario
1.4.4.4 | Manual de usuario
1.4.4.5 | Capacitación
1.5 | Migración
1.5.1 | Planificación
1.5.2 | Planes de contingencia
|  | Total Actual Cost | 4700000 | 1140000 | 30000 | 900000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 4700000 | 5840000 | 5870000 | 6770000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000 | 7370000