## PV
[Project Title] | [13 empty] | [Company Name / Logo]
Earned Value Analysis Report
| Prepared By: | [Manager's Name]
| Date: | [Report Date]
[42]
| For Period: | Week 1
Summary:
El periodo indica semana terminada
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | Tarea 0 | 100 |  | 100 | [13 empty] | ← Enter or edit values in the light-blue cells.
1.2 | Tarea 1 | 1000 |  | 500 | 500
1.3 | Tarea 2 | 2500 |  |  | 1000 | 1500
1.4 | Tarea 3 | 2400 |  |  |  | 1500 | 900
0
0
0
0
0
Insert new rows above this one | [17 empty] | ← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost | 6000 | 0 | 600 | 1500 | 3000 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Planned Value (PV) | 0 | 600 | 2100 | 5100 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | Línea azul en el gráfico
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 20 | 450 | 1800 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | Línea roja en el gráfico
|  | Cumulative Earned Value (EV) | 20 | 480 | 1400 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Línea verde en el gráfico
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 0 | 30 | -400 | -1600 | -4250 | -4250 | -4250 | -4250 | -4250 | -4250 | -4250 | -4250 | -4250 | -4250
|  | Schedule Variance (SV = EV - PV) | 20 | -120 | -700 | -2450 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000
|  | Cost Performance Index (CPI = EV/AC) | 1 | 1.0667 | 0.77778 | 0.62353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Schedule Performance Index (SPI = EV/PV) | #DIV/0! | 0.8 | 0.66667 | 0.51961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Estimated Cost at Completion (EAC) | 6000 | 5625 | 7714.2857 | 9622.6415 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Fecha oficial inicio de proyectos |  |  | 2015-04-10
Fecha presentación de proyectos terminados |  |  | 2015-07-17
Total semanas |  |  | 14
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)
Note on D21: profesor: 10/04/15 al 17/04/15

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Tarea 0 | 100 | 20% | 80%
1.2 | Tarea 1 | 1000 |  | 40% | 40% | 20%
1.3 | Tarea 2 | 2500 |  |  | 40% | 50%
1.4 | Tarea 3 | 2400 |  |  |  | 50%
- | - | 0
- | - | 0
#REF!
#REF!
#REF!
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 20 | 480 | 1400 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Tarea 0 |  | Wk 1: 20; Wk 2: 80
1.2 | Tarea 1 |  | Wk 2: 350; Wk 3: 400; Wk 4: 150
1.3 | Tarea 2 |  | Wk 3: 950; Wk 4: 1000
1.4 | Tarea 3 |  | Wk 4: 1300
- | -
- | -
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 20 | 430 | 1350 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 20 | 450 | 1800 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250